## Instructions
TIB SYSTEMS LLC ¦ SAP Controls Project Foundation Workbook Set
W04 — Risk Register
Purpose
States, for each in-scope process and technical area, what could go wrong, who owns the risk and how significant it is. A risk is an exposure, never a finding: nothing here says a control has failed.
How to use this workbook
1. Paste the BP-IDs from W03 (BP_Index tab, values only) into the Ref_BP tab.
2. Start from the TIB risk library or the client RCM; tailor to each process and technical area.
3. Write each risk with the formula: There is a risk that … because … resulting in …
4. Assign category, assertions, owner and likelihood/impact. Mark SOX-relevant risks.
5. Agree owners with the business and read the Checks tab.
Colour legend
Yellow cells with blue text = you enter data here. Grey cells = formulas (do not overwrite). Row 5 of each register is a worked ABC Manufacturing example: overwrite it with your first record.
Completion gate
Every in-scope BP-ID, including technical areas, has at least one risk.
Every risk follows the formula, has a category, assertions and a risk owner (or TBC).
SOX-relevant risks are flagged.
No risk statement contains an effectiveness conclusion.
Manual reference
Part 1, Session 5 (W04).
Column dictionary
Tab | Field | Definition | Allowed values / rule | Type
Risk_Register | RISK-ID | Unique key | R-<process>-nnn | Input
Risk_Register | BP-ID | Process or technical area the risk belongs to | Must exist in W03 (Ref_BP) | Input
Risk_Register | SYS-ID / INT-ID | System or interface where the risk arises | Keys from W01 / W02 | Input
Risk_Register | Risk category | Type of risk; guides control category in W05 | Dropdown | Input
Risk_Register | Risk statement | What could go wrong | "There is a risk that … because … resulting in …"; never a finding | Input
Risk_Register | Assertion(s) | Financial statement assertions affected | Occurrence, Completeness, Accuracy, Cut-off, Valuation, Existence, Rights & obligations, Presentation | Input
Risk_Register | Risk owner | Accountable for the outcome | Name / role; TBC allowed | Input
Risk_Register | Inherent likelihood | Before controls | 1 Low / 2 Medium / 3 High | Input
Risk_Register | Inherent impact | Before controls | 1 Low / 2 Medium / 3 High | Input
Risk_Register | Inherent rating | Likelihood × impact | Formula; 1–9 | Formula
Risk_Register | Rating band | High ≥ 6, Medium 3–5, Low < 3 | Formula | Formula
Risk_Register | SOX relevant? | Could lead to a material misstatement | Y / N; drives key-control requirement in W05 | Input
Risk_Register | Risk source | Where the risk came from | Dropdown | Input
Risk_Register | Status | Agreement status | No "Failed" value exists | Input
Risk_Register | Notes | Limitations or follow-ups | Free text | Input
Risk_Register | Row check | Automatic completeness test | Formula | Formula
Version history
0.1 — October 2026 — initial template (TIB Systems LLC)
Cross-workbook links: keys from other workbooks are pasted as values into the Ref_ tabs, so this file works on its own and never breaks when files are moved.

## Risk_Register
W04 — Risk Register
One row per risk. Row 5 is a worked example (R-P2P-001). Overwrite it.
RISK-ID | BP-ID | SYS-ID / INT-ID | Risk category | Risk statement | Assertion(s) | Risk owner | Inherent likelihood | Inherent impact | Inherent rating | Rating band | SOX relevant? | Risk source | Status | Notes | Row check
R-P2P-001 | BP-P2P-01 | SYS-03 | SoD | There is a risk that a fictitious vendor is created and paid because one user can both maintain vendor master data and execute the payment run, resulting in fraudulent payments and overstated expenses. | Occurrence | Head of AP | 3 | 3 | 9 | High | Y | Client RCM | Agreed with owner |  | OK

## Coverage_By_BP
Coverage by BP-ID
Every in-scope BP-ID (Ref_BP) must have at least one risk. All cells are formulas.
BP-ID | Risks | High-band risks | SOX-relevant risks | Status
BP-R2R-01 | 0 | 0 | 0 | NO RISK: add a risk
BP-R2R-02 | 0 | 0 | 0 | NO RISK: add a risk
BP-P2P-01 | 1 | 1 | 1 | OK
BP-P2P-02 | 0 | 0 | 0 | NO RISK: add a risk
BP-P2P-03 | 0 | 0 | 0 | NO RISK: add a risk
BP-INV-01 | 0 | 0 | 0 | NO RISK: add a risk
BP-O2C-01 | 0 | 0 | 0 | NO RISK: add a risk
BP-O2C-02 | 0 | 0 | 0 | NO RISK: add a risk
BP-H2R-01 | 0 | 0 | 0 | NO RISK: add a risk
BP-TECH-01 | 0 | 0 | 0 | NO RISK: add a risk
BP-TECH-02 | 0 | 0 | 0 | NO RISK: add a risk
BP-TECH-03 | 0 | 0 | 0 | NO RISK: add a risk

## Ref_BP
Paste BP-IDs from W03 (values only, column A)
BP-R2R-01
BP-R2R-02
BP-P2P-01
BP-P2P-02
BP-P2P-03
BP-INV-01
BP-O2C-01
BP-O2C-02
BP-H2R-01
BP-TECH-01
BP-TECH-02
BP-TECH-03

## Lists (hidden)
Cat | L3 | YN | Src | RStat
ITGC-APD | 1 | Y | Client RCM | Draft
ITGC-PC | 2 | N | TIB risk library | Agreed with owner
ITGC-CO | 3 |  | Walkthrough | Dependency open
ITGC-PD |  |  | Prior-year audit issue
ITAC |  |  | W01–W03 gap
SoD
Business process
IPE
Interface

## Checks
W04 — Completion checks
All checks are formulas. A workbook passes its gate when every status reads PASS (INFO rows are counts for your information).
Overall | REVIEW ITEMS: 2
Check | Count | Status | What to do if REVIEW
Risks recorded | 1 | INFO | —
Duplicate RISK-IDs | 0 | PASS | Keys must be unique.
Register rows needing attention | 0 | PASS | Read the Row check column.
In-scope BP-IDs with no risk | 11 | REVIEW | Walk through the process with its owner and add risks.
SOX-relevant risks | 1 | INFO | Each needs at least one key control in W05.
High-band risks | 1 | INFO | Prioritise in the test plan.
Risks not yet agreed with owner | 0 | INFO | Agree owner and rating (gate G3).
Technical-area risks recorded (BP-TECH) | 0 | REVIEW | ITGC risks must exist for access, change and operations.