## Instructions
TIB SYSTEMS LLC ¦ SAP Controls Project Foundation Workbook Set
W07 — Control & Evidence Owner Matrix
Purpose
Records, for every control in the RCM, who is accountable for it, who performs it, who can provide the evidence and who the backup is. These are often different people. Keyed by CTRL-ID so it lines up one-to-one with W05.
How to use this workbook
1. Paste CTRL-ID, title, evidence expectation, key flag and risk owner from W05/W04 into Ref_CTRL.
2. Add one Owner_Matrix row per CTRL-ID. Pre-fill the control owner from W05.
3. Meet each owner. Ask two questions: who makes sure this happens, and who can give us the evidence?
4. Record walkthrough contacts for key controls.
5. Mark unresolved items Outstanding with a follow-up, never as a control failure.
Colour legend
Yellow cells with blue text = you enter data here. Grey cells = formulas (do not overwrite). Row 5 of each register is a worked ABC Manufacturing example: overwrite it with your first record.
Completion gate
Every in-scope CTRL-ID has a row.
Control owner and evidence owner are identified or marked Outstanding.
Walkthrough contacts are known for every key control.
Outstanding owners are escalated in the W14 dependency list.
Manual reference
Part 2, Session 8 (W07).
Column dictionary
Tab | Field | Definition | Allowed values / rule | Type
Owner_Matrix | CTRL-ID | Control from the RCM | Must exist in W05 (Ref_CTRL) | Input
Owner_Matrix | Control title | Lookup from W05 | Formula | Formula
Owner_Matrix | Key control? | Lookup from W05 | Formula | Formula
Owner_Matrix | Risk owner | Lookup from W04 via Ref_CTRL | Formula | Formula
Owner_Matrix | Control owner | Accountable for the control operating | Required, or mark Outstanding | Input
Owner_Matrix | Control performer | Person who executes it day to day | May equal owner | Input
Owner_Matrix | Evidence owner | Person or team who can produce the evidence | Required, or mark Outstanding | Input
Owner_Matrix | Backup contact | Alternate for leave or turnover | Recommended | Input
Owner_Matrix | Primary SYS-ID | Where evidence resides | From W01 | Input
Owner_Matrix | Expected evidence | Lookup from W05 | Formula | Formula
Owner_Matrix | Walkthrough contact | Person who will demonstrate the control in TOD | Usually the performer | Input
Owner_Matrix | Owner status | Confirmation state; Outstanding is not a failure | Confirmed / Outstanding | Input
Owner_Matrix | Date confirmed | When the owner agreed | Date; required if Confirmed | Input
Owner_Matrix | Follow-up | What still needs resolving | Required if Outstanding | Input
Owner_Matrix | Row check | Automatic completeness test | Formula | Formula
Open_Items | Item ID | Unique open-item reference | OI-nn | Input
Open_Items | Source | Workbook and key the question comes from | e.g. SYS-05 | Input
Open_Items | Question / dependency | What must still be confirmed | Free text | Input
Open_Items | Owner | Person who can answer | Name / role | Input
Open_Items | Raised | Date raised | Date | Input
Open_Items | Target date | Date needed by | Date | Input
Open_Items | Status | Progress | Open / In progress / Closed | Input
Open_Items | Resolution | How it was resolved | Free text | Input
Version history
0.1 — October 2026 — initial template (TIB Systems LLC)
Cross-workbook links: keys from other workbooks are pasted as values into the Ref_ tabs, so this file works on its own and never breaks when files are moved.

## Owner_Matrix
W07 — Owner Matrix
One row per control. Row 5 is a worked example. Overwrite it.
CTRL-ID | Control title | Key control? | Risk owner | Control owner | Control performer | Evidence owner | Backup contact | Primary SYS-ID | Expected evidence | Walkthrough contact | Owner status | Date confirmed | Follow-up | Row check
C-ITAC-004 | Three-way match blocks out-of-tolerance invoices | Y | Head of AP | Head of AP | System (automated) | SAP functional support | SAP functional lead | SYS-03 | OMR6 screenshot, table change log, blocked invoice sample | SAP functional lead | Confirmed | 2026-10-01 |  | OK

## Open_Items
W07 — Open Items
Ownership or evidence questions still to resolve.
Item ID | Source | Question / dependency | Owner | Raised | Target date | Status | Resolution
OI-01 | C-ITGC-AC-004 | Controller list for Firefighter IDs not yet provided | IT Security Manager |  |  | Open

## Ref_CTRL
CTRL-ID (from W05) | Control title (from W05) | Control owner (from W05) | Expected evidence (from W05) | Key control? Y/N (from W05) | Risk owner (from W04)
C-ITAC-004 | Three-way match blocks out-of-tolerance invoices | Head of AP | OMR6 screenshot, table change log, blocked invoice sample | Y | Head of AP
C-ITGC-AC-002 | Timely removal of leavers | IT Security Manager | HR leavers report; SU01 change documents | Y | IT Security Manager
C-ITGC-AC-003 | Quarterly user access review | IT Security Manager | UAR campaign export, sign-offs, removal evidence | Y | IT Security Manager
C-ITGC-AC-004 | Firefighter use approved and reviewed | IT Security Manager | EAM session logs, approvals, controller review | Y | IT Security Manager
C-ITGC-PC-001 | Transports approved, tested, imported by Basis | Basis Lead | STMS import history; change tickets | Y | Basis Lead
C-BPC-P2P-003 | Payment file reconciliation | Treasury Manager | Bank confirmations, F110 logs | Y | Treasury Manager

## Lists (hidden)
OStat | OpenStatus
Confirmed | Open
Outstanding | In progress
Closed

## Checks
W07 — Completion checks
All checks are formulas. A workbook passes its gate when every status reads PASS (INFO rows are counts for your information).
Overall | REVIEW ITEMS: 1
Check | Count | Status | What to do if REVIEW
Controls with an owner row | 1 | INFO | —
Duplicate CTRL-IDs | 0 | PASS | One row per control.
Rows needing attention | 0 | PASS | Read the Row check column.
W05 controls with no owner-matrix row | 5 | REVIEW | Every in-scope CTRL-ID needs a row.
Owners still Outstanding | 0 | INFO | Escalate in the W14 dependency list. Not a control failure.
Key controls with owner not yet confirmed | 0 | INFO | Prioritise before gate G5.
Rows with no backup contact | 0 | INFO | Recommended: identify an alternate.
Open items still open | 1 | INFO | Track to closure.