## Instructions
TIB SYSTEMS LLC ¦ SAP Controls Project Foundation Workbook Set
W08 — PBC / Evidence Request Register
Purpose
Lists every piece of evidence requested, from whom, for which period and for which control and test. Every request must answer a future testing question. If it cannot be traced to a CTRL-ID and a planned test, do not make it.
How to use this workbook
1. Paste CTRL-ID, title, evidence owner (W07), key flag (W05) into Ref_CTRL.
2. For each in-scope key control, read Expected evidence and Test approach in W05 and write the wave 1 and 2 requests (configuration and populations).
3. Make each request precise: system, client, period, fields, format. Consolidate requests that serve several controls.
4. Issue, then track daily. Update Status and add EV-IDs as items are indexed in W09.
5. Raise wave 3 sample requests only after W12 sampling is complete.
Colour legend
Yellow cells with blue text = you enter data here. Grey cells = formulas (do not overwrite). Row 5 of each register is a worked ABC Manufacturing example: overwrite it with your first record.
Completion gate
Every request traces to at least one CTRL-ID (and TEST-ID once W10 exists).
Every request states system, period and required fields.
Population requests are flagged for IPE checks.
Outstanding requests are visible with owner and due date.
Manual reference
Part 2, Session 9 (W08).
Column dictionary
Tab | Field | Definition | Allowed values / rule | Type
PBC_Register | PBC-ID | Unique key | PBC-nnn | Input
PBC_Register | Request wave | Timing of the request | 1 Scoping / 2 Population / 3 Sample / 4 Follow-up | Input
PBC_Register | Primary CTRL-ID | Main control the evidence supports | Must exist in W05 | Input
PBC_Register | Other CTRL-ID(s) | Other controls served by the same request | CTRL-ID list | Input
PBC_Register | TEST-ID(s) | Tests that will use it | Back-filled when W10 is built; required for wave 3 | Input
PBC_Register | BP-ID / SYS-ID | Where the evidence applies | Keys from W03 / W01 | Input
PBC_Register | Requested evidence | Exactly what is needed: system, client, period, fields, format | Specific enough to be unambiguous | Input
PBC_Register | Period from | Start of period or as-of date | Date | Input
PBC_Register | Period to | End of period | Date | Input
PBC_Register | Evidence type | Request type; Population triggers an IPE check | Population / Sample / Configuration / Policy | Input
PBC_Register | Evidence owner | From W07 (lookup via Ref_CTRL) | Formula | Formula
PBC_Register | Date requested | Tracking | Date | Input
PBC_Register | Due date | Agreed due date | Date | Input
PBC_Register | Priority | Urgency; High for populations | High / Medium / Low | Input
PBC_Register | Status | Progress | Dropdown | Input
PBC_Register | EV-ID(s) | Evidence received, once indexed in W09 | Required once Received | Input
PBC_Register | IPE needed? | Population requests need completeness and accuracy checks | Formula | Formula
PBC_Register | Days overdue | Today minus due date while not received | Formula | Formula
PBC_Register | Notes | Completeness requirements or follow-up | Free text | Input
PBC_Register | Row check | Automatic completeness test | Formula | Formula
Version history
0.1 — October 2026 — initial template (TIB Systems LLC)
Cross-workbook links: keys from other workbooks are pasted as values into the Ref_ tabs, so this file works on its own and never breaks when files are moved.

## PBC_Register
W08 — PBC Register
One row per request. Row 5 is a worked example. Overwrite it.
PBC-ID | Request wave | Primary CTRL-ID | Other CTRL-ID(s) | TEST-ID(s) | BP-ID / SYS-ID | Requested evidence | Period from | Period to | Evidence type | Evidence owner | Date requested | Due date | Priority | Status | EV-ID(s) | IPE needed? | Days overdue | Notes | Row check
PBC-018 | 2 Population | C-ITGC-PC-001 |  |  | SYS-03 | STMS import history to ECP/300: all transports imported 01-Jan to 30-Sep (TPALOG). CSV with request number, import date/time, importing user, return code. | 2026-01-01 | 2026-09-30 | Population | Basis; ITSM admin | 2026-10-01 | 2026-10-09 | High | Requested |  | Y | 0 | Confirm no filters applied to extract | OK
Formulas:
Days overdue = IF(OR([PBC-ID]="",[Due date]="",[Status]="Received",[Status]="Closed"),"",IF(TODAY()>[Due date],TODAY()-[Due date],0))

## Ref_CTRL
CTRL-ID (from W05) | Control title (from W05) | Evidence owner (from W07) | Expected evidence (from W05) | Key control? Y/N (from W05)
C-ITAC-004 | Three-way match blocks out-of-tolerance invoices | SAP functional support | OMR6 screenshot, table change log | Y
C-ITGC-AC-002 | Timely removal of leavers | HR Operations; Basis | HR leavers report; SU01 change documents | Y
C-ITGC-AC-003 | Quarterly user access review | GRC Administrator | UAR campaign export | Y
C-ITGC-PC-001 | Transports approved, tested, imported by Basis | Basis; ITSM admin | STMS import history; change tickets | Y

## Lists (hidden)
Wave | EType | Pri | PStat
1 Scoping | Population | High | Requested
2 Population | Sample | Medium | Partially received
3 Sample | Configuration | Low | Received
4 Follow-up | Policy |  | Rejected - incomplete
Closed

## Checks
W08 — Completion checks
All checks are formulas. A workbook passes its gate when every status reads PASS (INFO rows are counts for your information).
Overall | REVIEW ITEMS: 1
Check | Count | Status | What to do if REVIEW
PBC requests raised | 1 | INFO | —
Duplicate PBC-IDs | 0 | PASS | Keys must be unique.
Request rows needing attention | 0 | PASS | Read the Row check column.
Key controls with NO PBC request (primary control) | 3 | REVIEW | Every key control needs evidence requested; read Expected evidence in W05.
Population requests (need IPE check in W09) | 1 | INFO | Complete completeness and accuracy checks before sampling.
Requests overdue | 0 | INFO | Chase evidence owners daily during fieldwork.
Requests Requested / Partially received | 1 | INFO | Outstanding items go to the W14 dependency list.
Requests rejected as incomplete | 0 | INFO | Return to the evidence owner with the gap stated.
Requests Received or Closed | 0 | INFO | Each must carry an EV-ID.