## Instructions
TIB SYSTEMS LLC ¦ SAP Controls Project Foundation Workbook Set
W10 — Test Plan / Testing Program
Purpose
Converts the RCM into a schedule of tests. Every in-scope key control gets a test of design (TOD) and a test of operating effectiveness (TOE) with attributes, procedure, population, sample size, period, tester, reviewer and dates.
How to use this workbook
1. Paste controls from W05 into Ref_CTRL, and evidence IDs with IPE result and record count from W09 into Ref_EV.
2. Filter W05 for SOX in scope = Y. Create a TOD and a TOE row for each key control; derive attributes from the control description.
3. Set sample size from the Sample_Guide (edit the guide to match engagement methodology). Mark ITGC reliance.
4. Assign testers and reviewers (different people). Schedule ITGC tests before dependent ITAC/IPE tests.
5. Update Status and Result only after review. Read the Checks tab.
Colour legend
Yellow cells with blue text = you enter data here. Grey cells = formulas (do not overwrite). Row 5 of each register is a worked ABC Manufacturing example: overwrite it with your first record.
Completion gate
Every SOX in-scope key control has a TOD and a TOE row.
Every row has attributes derived from the control description.
Sample sizes follow the guide or a justified deviation.
ITGC tests are scheduled before dependent ITAC/IPE tests.
Manual reference
Part 2, Session 11 (W10).
Column dictionary
Tab | Field | Definition | Allowed values / rule | Type
Test_Plan | TEST-ID | Unique key | <CTRL-ID>-TOD or -TOE | Input
Test_Plan | CTRL-ID | Control being tested | From W05 (Ref_CTRL) | Input
Test_Plan | Control title | Lookup | Formula | Formula
Test_Plan | Control category | Lookup; drives workpaper template | Formula | Formula
Test_Plan | Frequency | Lookup; drives sample size | Formula | Formula
Test_Plan | Test type | TOD or TOE | One TOD and one TOE per key control | Input
Test_Plan | Test attributes | Conditions each sample item must meet | Lettered A, B, C…; derived from the control description | Input
Test_Plan | Test procedure | What the tester does | Inquiry / Observation / Inspection / Reperformance; inquiry alone is never enough | Input
Test_Plan | Population EV-ID | Population sampled from (TOE) | IPE must be Pass | Input
Test_Plan | IPE result | Lookup from W09 | Formula | Formula
Test_Plan | Population size | Lookup from W09 | Formula | Formula
Test_Plan | Guide sample | Typical range for the frequency | Formula | Formula
Test_Plan | Sample size | Items to test | Number; justify deviations from the guide | Input
Test_Plan | Test period from | Start of period | Date | Input
Test_Plan | Test period to | End of period | Date | Input
Test_Plan | ITGC reliance needed? | Dependent controls need effective ITGCs | Formula | Formula
Test_Plan | Tester | Who performs | Name | Input
Test_Plan | Reviewer | Who reviews; must differ from tester | Name | Input
Test_Plan | Planned start | Schedule | Date | Input
Test_Plan | Planned end | Schedule | Date | Input
Test_Plan | Workpaper ref | W11 workpaper | File name or WP ref | Input
Test_Plan | Status | Progress | Dropdown | Input
Test_Plan | Result | Outcome (only after review) | Dropdown | Input
Test_Plan | Row check | Automatic completeness test | Formula | Formula
Version history
0.1 — October 2026 — initial template (TIB Systems LLC)
Cross-workbook links: keys from other workbooks are pasted as values into the Ref_ tabs, so this file works on its own and never breaks when files are moved.

## Test_Plan
W10 — Test Plan
One row per test. Rows 5–6 are worked examples. Overwrite them.
TEST-ID | CTRL-ID | Control title | Control category | Frequency | Test type | Test attributes | Test procedure | Population EV-ID | IPE result | Population size | Guide sample | Sample size | Test period from | Test period to | ITGC reliance needed? | Tester | Reviewer | Planned start | Planned end | Workpaper ref | Status | Result | Row check
C-ITGC-PC-001-TOE | C-ITGC-PC-001 | Transports approved, tested, imported by Basis | ITGC-PC | Event-driven | TOE | A Change ticket approved before import ¦ B QAS test and business sign-off ¦ C Imported by user other than the developer ¦ D Content agrees to approved change ¦ E Emergency changes approved within 2 business days | Inspection of ticket, QAS import and TPALOG record for each sampled transport | EV-019 | Pass | 312 | 25–60 | 25 | 2026-01-01 | 2026-09-30 | N | Tester 1 | Manager 1 | 2026-10-12 | 2026-10-16 | WP-PC-01_C-ITGC-PC-001-TOE | Not started | Not started | OK
C-ITGC-PC-001-TOD | C-ITGC-PC-001 | Transports approved, tested, imported by Basis | ITGC-PC | Event-driven | TOD | Walkthrough of one normal and one emergency change from ticket to import | Inquiry with Change Manager plus inspection of one change end to end |  |  |  | 1 |  | 2026-01-01 | 2026-09-30 | N | Tester 1 | Manager 1 | 2026-10-05 | 2026-10-06 | WP-PC-01_C-ITGC-PC-001-TOD | Not started | Not started | OK

## Sample_Guide
Sample Guide (editable)
Typical SOX sample sizes. Always apply the engagement firm or external auditor methodology where one is specified; edit the values to match.
Control frequency | Typical population | Guide low | Guide high | Note
Annual | 1 | 1 | 1
Quarterly | 4 | 2 | 2
Monthly | 12 | 2 | 5
Weekly | 52 | 5 | 15
Daily | 250 | 20 | 40
Event-driven | 300 | 25 | 60 | More than 250 occurrences
Continuous |  | 1 | 1 | Automated (ITAC): 1 per configuration if dependent ITGCs are effective

## Ref_CTRL
CTRL-ID (from W05) | Control title | Control category | Frequency | Key control? (Y/N) | SOX in scope? (Y/N)
C-ITGC-PC-001 | Transports approved, tested, imported by Basis | ITGC-PC | Event-driven | Y | Y
C-ITGC-AC-002 | Timely removal of leavers | ITGC-APD | Event-driven | Y | Y
C-ITAC-004 | Three-way match blocks out-of-tolerance invoices | ITAC | Continuous | Y | Y

## Ref_EV
EV-ID (from W09) | IPE result (W09) | Record count (W09)
EV-012 | Pass | 1284
EV-019 | Pass | 312
EV-021 | Pending | 48

## Lists (hidden)
TType | TStat | TRes
TOD | Not started | Not started
TOE | In progress | Effective
| Ready for review | Exception noted
| Reviewed | Ineffective
Closed

## Checks
W10 — Completion checks
All checks are formulas. A workbook passes its gate when every status reads PASS (INFO rows are counts for your information).
Overall | REVIEW ITEMS: 2
Check | Count | Status | What to do if REVIEW
Test rows | 2 | INFO | —
Duplicate TEST-IDs | 0 | PASS | Keys must be unique.
Test rows needing attention (incl. HOLD) | 0 | PASS | Read the Row check column.
Key controls with NO test of design | 2 | REVIEW | Every key control needs a TOD row.
Key controls with NO test of operating effectiveness | 2 | REVIEW | Every key control needs a TOE row.
Dependent (ITAC/IPE/ITDM) TOE tests (excluding retests) planned to start before the last ITGC TOE ends | 0 | PASS | Schedule ITGC operating tests first: their results decide how much reliance ITACs can have.
Tests not started | 2 | INFO | Track against the plan.
Tests reviewed or closed | 0 | INFO | Results flow to W13 and W14.
Tests with an exception or ineffective result | 0 | INFO | Each needs a DEF-ID or false-positive rationale (W13).