## Instructions
TIB SYSTEMS LLC ¦ SAP Controls Project Foundation Workbook Set
W13 — Deficiency & Remediation Log
Purpose
Records every confirmed test exception, evaluates its severity (condition, criteria, cause, effect), links it back through the thread to the risk and process, groups related deficiencies, and tracks remediation and retest.
How to use this workbook
1. Paste TEST-ID, CTRL-ID, RISK-ID, BP-ID and the W10 result into Ref_TEST.
2. Validate each exception first: false positive, wrong population or later evidence? Only confirmed exceptions get a DEF-ID.
3. Write the four-part statement, record compensating controls and dependent controls affected, and set severity.
4. Aggregate related deficiencies in Groups (same user, date, process or cause) and evaluate the group.
5. Record management response, owner and due date; add the retest TEST-ID. A deficiency closes only after a successful retest.
Colour legend
Yellow cells with blue text = you enter data here. Grey cells = formulas (do not overwrite). Row 5 of each register is a worked ABC Manufacturing example: overwrite it with your first record.
Completion gate
Every confirmed exception has a DEF-ID traced to test, control, risk and process.
Severity is evaluated, including impact on dependent controls and compensating controls.
Management response, owner and due date are recorded.
Retest is planned for every remediated deficiency.
Manual reference
Part 4, Sessions 35–37 (W13).
Column dictionary
Tab | Field | Definition | Allowed values / rule | Type
Deficiency_Log | DEF-ID | Unique key | DEF-nnn | Input
Deficiency_Log | TEST-ID | Test where it was found | From W10 (Ref_TEST) | Input
Deficiency_Log | CTRL-ID | Lookup | Formula | Formula
Deficiency_Log | RISK-ID | Lookup | Formula | Formula
Deficiency_Log | BP-ID | Lookup | Formula | Formula
Deficiency_Log | Deficiency type | Design or operating | Design / Operating | Input
Deficiency_Log | Condition | What was found (facts, numbers, dates) | Four-part statement | Input
Deficiency_Log | Criteria | What should have happened | Control description or policy | Input
Deficiency_Log | Cause | Why it happened (from inquiry) | Free text | Input
Deficiency_Log | Effect | What could go wrong; link to risk and assertion | Free text | Input
Deficiency_Log | Exceptions | Failed items out of sample | e.g. 3 of 25 | Input
Deficiency_Log | Dependent controls affected | ITAC / IPE / ITDM relying on this ITGC | From W05 ITGC_Dependency | Input
Deficiency_Log | Compensating controls | Other controls reducing the exposure | CTRL-ID list | Input
Deficiency_Log | Compensating tested effective? | Result of testing the compensating control | Y / N / Pending | Input
Deficiency_Log | Severity | Evaluated level | Control deficiency / Significant deficiency / Material weakness | Input
Deficiency_Log | Group ID | Aggregation group | From Groups tab | Input
Deficiency_Log | Management response | Owner's agreed action | Free text | Input
Deficiency_Log | Remediation owner | Who fixes it | Name / role | Input
Deficiency_Log | Due date | Remediation due | Date | Input
Deficiency_Log | Retest TEST-ID | Test confirming the fix | e.g. <CTRL-ID>-RT1 | Input
Deficiency_Log | Status | Progress | Dropdown | Input
Deficiency_Log | Row check | Automatic completeness test | Formula | Formula
Groups | Group ID | Unique key | GR-x | Input
Groups | Group name | Short name | e.g. Privileged access governance | Input
Groups | Common factor | What links the deficiencies | Same user, date, process, root cause | Input
Groups | Evaluated exposure | Combined exposure after compensating controls and follow-up | Free text | Input
Groups | Group severity | Severity of the group | Reviewer approved | Input
Groups | Rationale | Why this severity | Magnitude, likelihood, compensating controls, reliance | Input
Groups | DEFs in group | Count | Formula | Formula
Groups | Highest individual severity | Highest rating among its DEFs | Formula | Formula
Groups | Check | Automatic test | Formula | Formula
Version history
0.1 — October 2026 — initial template (TIB Systems LLC)
Cross-workbook links: keys from other workbooks are pasted as values into the Ref_ tabs, so this file works on its own and never breaks when files are moved.

## Deficiency_Log
W13 — Deficiency Log
One row per deficiency. Rows 5–6 are worked examples (DEF-004, DEF-007). Overwrite them.
DEF-ID | TEST-ID | CTRL-ID | RISK-ID | BP-ID | Deficiency type | Condition | Criteria | Cause | Effect | Exceptions | Dependent controls affected | Compensating controls | Compensating tested effective? | Severity | Group ID | Management response | Remediation owner | Due date | Retest TEST-ID | Status | Row check
DEF-004 | C-ITGC-AC-002-TOE | C-ITGC-AC-002 | R-TECH-001 | BP-TECH-01 | Operating | 3 of 25 sampled leavers locked 6 to 14 business days after termination; one display-only logon after termination date | Leavers locked within two business days of HR termination (C-ITGC-AC-002) | HR leavers report is sent weekly, not daily | Leavers retain ability to post transactions (R-TECH-001, Occurrence) | 3 of 25 |  | C-ITGC-AC-003 | Y | Control deficiency | GR-C | Agreed: daily HR feed to GRC with automatic lock | IT Security Manager | 2026-12-31 | C-ITGC-AC-002-RT1 | Open | OK
DEF-007 | C-ITGC-AC-005-TOE | C-ITGC-AC-005 | R-TECH-005 | BP-TECH-01 | Operating | Dialog user FI_SUPPORT1 holds SAP_ALL; generic ID TRAINING01 active; June privileged-access review not evidenced | Privileged access restricted to approved users and reviewed monthly (C-ITGC-AC-005) | Emergency fix on 14-Mar outside the access process; no retrospective review | Basis can bypass change and access controls (R-TECH-003, R-TECH-005) | 1 SAP_ALL holder; 1 generic ID; 1 of 3 reviews | C-ITAC-004, C-ITAC-005 | Full-period table logs and usage analysis | Y | Control deficiency | GR-A | Agreed: remove SAP_ALL from dialog users; use Firefighter | Basis Lead | 2026-11-30 | C-ITGC-AC-005-RT1 | Open | OK

## Groups
W13 — Aggregation Groups
Evaluate related deficiencies together. Rows 5–6 are worked examples.
Group ID | Group name | Common factor | Evaluated exposure | Group severity | Rationale | DEFs in group | Highest individual severity | Check
GR-A | Privileged access governance | Same user type (Basis), same date (14-Mar), emergency fix outside process | Change and access controls can be bypassed by Basis; full-period table logs and usage analysis show no misuse | Significant deficiency | Pervasive potential to bypass change and access controls; no evidence of misuse; ITAC reliance restored, so not a material weakness | 1 | Control deficiency | OK
GR-C | Access hygiene | Timeliness and precision of access controls | Compensated by the effective quarterly access review | Control deficiency | Compensating control tested effective and precise within a quarter | 1 | Control deficiency | OK

## Ref_TEST
TEST-ID (from W10) | CTRL-ID (W10) | RISK-ID (W04 via W05) | BP-ID (W04) | Result (W10)
C-ITGC-AC-002-TOE | C-ITGC-AC-002 | R-TECH-001 | BP-TECH-01 | Exception noted
C-ITGC-AC-005-TOE | C-ITGC-AC-005 | R-TECH-005 | BP-TECH-01 | Ineffective
C-ITGC-PC-001-TOE | C-ITGC-PC-001 | R-TECH-003 | BP-TECH-02 | Exception noted
C-ITAC-004-TOE | C-ITAC-004 | R-P2P-002 | BP-P2P-02 | Effective

## Lists (hidden)
DType | YNP | Sev | DStat
Design | Y | Control deficiency | Draft
Operating | N | Significant deficiency | Open
| Pending | Material weakness | Remediation in progress
Retest
Closed

## Checks
W13 — Completion checks
All checks are formulas. A workbook passes its gate when every status reads PASS (INFO rows are counts for your information).
Overall | REVIEW ITEMS: 1
Check | Count | Status | What to do if REVIEW
Deficiencies logged | 2 | INFO | —
Duplicate DEF-IDs | 0 | PASS | Keys must be unique.
Deficiency rows needing attention | 0 | PASS | Read the Row check column.
Group rows needing attention | 0 | PASS | Read the Check column.
Tests with an exception / ineffective result and NO DEF-ID | 1 | REVIEW | Raise a DEF, or record a false-positive rationale in the W11 workpaper and clear the W10 result.
Open material weaknesses | 0 | INFO | Escalate to the partner and audit committee.
Open significant deficiencies | 0 | INFO | Report to those charged with governance.
Open control deficiencies | 2 | INFO | —
Remediation overdue | 0 | INFO | Chase the remediation owner.
Deficiencies awaiting retest | 0 | INFO | Create the retest in W10.