## 01_Takeover_Plan
TIB Controls Lead - First 30-Day Takeover Plan
Day/Week | Priority | Action / Question | Stakeholder | Evidence / Input Needed | Owner | Due Date | Status
Day 1 | Critical | Confirm sponsor expectations, project objectives, regulatory/audit deadlines and immediate concerns. | Executive Sponsor | Appointment brief; current status pack | Controls Lead |  | Not Started
Day 1-2 | Critical | Meet controls team; understand roles, open work, blockers and capacity. | Controls Team | Resource list; workplan; open actions | Controls Lead |  | Not Started
Day 2-3 | High | Review current project scope and all 14 foundation artifacts for completeness and traceability. | PMO / Workstream Leads | Current workbooks; prior review notes | Controls Lead |  | Not Started
Day 3-4 | High | Meet Internal Audit / External Audit to confirm requests, deadlines, unresolved questions and reliance expectations. | Audit | PBC list; prior findings; audit calendar | Controls Lead |  | Not Started
Day 5 | Critical | Issue first management status: what is known, unknown, at risk, overdue and decisions required. | Sponsor / Steering Committee | Validated status from team | Controls Lead |  | Not Started
Week 2 | High | Stabilize team assignments, review cadence, QA gates and escalation path. | Controls Team | RACI; QA checklist | Controls Lead |  | Not Started
Week 3 | High | Assess deficiencies, remediation ownership and aging; identify systemic issues. | Control Owners | Deficiency log; root-cause notes | Controls Lead |  | Not Started
Week 4 | Critical | Present 30-day assessment and 60/90-day roadmap. | Executive Sponsor | Executive dashboard; roadmap | Controls Lead |  | Not Started

## 02_RACI_Resource
Team RACI & Resource Delivery Plan
Deliverable / Activity | Responsible | Accountable | Consulted | Informed | Estimated Effort (Days) | Due Date | Status
Landscape and System Inventory | Analyst / SME | Controls Lead | Process / Technology Owner | Sponsor |  |  | Not Started
Interface and Data Flow Inventory | Analyst / SME | Controls Lead | Process / Technology Owner | Sponsor |  |  | Not Started
Module and Business Process Scope | Analyst / SME | Controls Lead | Process / Technology Owner | Sponsor |  |  | Not Started
Risk Register | Analyst / SME | Controls Lead | Process / Technology Owner | Sponsor |  |  | Not Started
Risk and Control Matrix | Analyst / SME | Controls Lead | Process / Technology Owner | Sponsor |  |  | Not Started
Separation of Duties and Sensitive Access Matrix | Analyst / SME | Controls Lead | Process / Technology Owner | Sponsor |  |  | Not Started
Control and Evidence Owner Matrix | Analyst / SME | Controls Lead | Process / Technology Owner | Sponsor |  |  | Not Started
Evidence Request Register | Analyst / SME | Controls Lead | Process / Technology Owner | Sponsor |  |  | Not Started
Evidence Index / IPE Log | Analyst / SME | Controls Lead | Process / Technology Owner | Sponsor |  |  | Not Started
Test Plan | Analyst / SME | Controls Lead | Process / Technology Owner | Sponsor |  |  | Not Started
Test Workpapers | Analyst / SME | Controls Lead | Process / Technology Owner | Sponsor |  |  | Not Started
Sample Selection Log | Analyst / SME | Controls Lead | Process / Technology Owner | Sponsor |  |  | Not Started
Deficiency and Remediation Log | Analyst / SME | Controls Lead | Process / Technology Owner | Sponsor |  |  | Not Started
Scoping Workpaper and Coverage Dashboard | Analyst / SME | Controls Lead | Process / Technology Owner | Sponsor |  |  | Not Started

## 03_QA_Review
Controls Lead QA Review Checklist
Artifact / Workpaper | Review Criterion | Reviewer Question | Finding | Disposition | Assigned To | Due Date | Closure Evidence
| Completeness | Is every required field, population, owner, period and conclusion present? |  | Pending
| Accuracy | Does the work reflect the source evidence and agreed facts? |  | Pending
| Support | Can every important assertion be traced to evidence, interview, configuration or source data? |  | Pending
| Traceability | Can we trace scope → risk → control → owner → evidence → test → conclusion? |  | Pending
| Risk Alignment | Does the control actually address the stated risk? |  | Pending
| Evidence Sufficiency | Is the evidence appropriate, complete, reliable and for the correct period/population? |  | Pending
| Testing Logic | Does the test procedure prove the control objective rather than merely describe the control? |  | Pending
| Conclusion | Is the conclusion supported by the work performed and exceptions identified? |  | Pending

## 04_Technical_Challenge
SAP Technical Challenge Guide
Domain | What the Lead Must Understand | Challenge Question | Expected Evidence / Demonstration | Red Flag | SME | Status | Notes
Landscape / S4 / RISE | Production/non-production landscape, hosting, responsibility boundaries | Show me which systems support the in-scope process and who is responsible for each control layer. | Landscape diagram; system inventory; RISE responsibility matrix | Unclear ownership between customer and provider |  | Not Started
SAP Security / IAM | User lifecycle, roles, approvals, privileged access | Show me how access is requested, approved, provisioned, changed and removed. | Access request; workflow; role assignment; leaver evidence | Manual provisioning with no independent approval |  | Not Started
SoD / GRC | Ruleset, risk analysis, mitigations, Firefighter | Show me how SoD conflicts are identified, approved, mitigated and reviewed. | ARA output; ruleset; mitigation; EAM logs | Mitigations never reviewed or Firefighter logs not reviewed |  | Not Started
Fiori | Catalogs, spaces/pages, backend authorizations | How do you ensure Fiori access and backend authorizations remain aligned? | Role design; catalog/space mapping; user assignment | Front-end visibility treated as equivalent to authorization |  | Not Started
Change / Transports | DEV-QA-PRD path, approvals, emergency change | Show me one production transport from request through approval and deployment. | Transport records; approvals; test evidence | Developer can move own change to production |  | Not Started
Interfaces / Jobs | Authentication, monitoring, failures, completeness | What happens when this interface or batch job fails, and who knows? | Job logs; interface monitor; incident records | No alerting or no reconciliation |  | Not Started
Reports / IPE | Completeness and accuracy of reports used in controls | How do we know this report population is complete and accurate? | Report parameters; source; reconciliation; validation | Screenshots without population validation |  | Not Started
BTP / Cloud | Identity, integrations, shared responsibility | Which controls remain with the customer and which sit with SAP/provider? | Architecture; contracts; SOC/service reports | Assuming provider owns all control responsibility |  | Not Started

## 05_Audit_Dashboard
Audit Request & Resolution Dashboard
Request ID | Auditor / Source | Request / Question | Internal Owner | Due Date | QA Status | Auditor Status | Resolution / Next Action
PBC-001 | External Audit | Provide access review population and evidence of quarterly review. | Security Manager |  | Not Reviewed | Open | Validate population before submission.
PBC-002 | Internal Audit | Explain prior-year SoD finding remediation status. | GRC Lead |  | Reviewed | Open | Confirm retest result and closure evidence.

## 06_Deficiency_Remediation
Management Deficiency & Remediation Register
Issue ID | Issue / Exception | Risk / Impact | Root Cause | Severity | Compensating Control | Remediation Owner | Target Date | Retest Status | Closure Evidence | Escalation Required | Management Decision
ISS-001 | Quarterly access review completed late. | Unauthorized access may remain undetected. | Ownership unclear after reorganization. | High | Monthly privileged access review partially reduces exposure. | Security Manager |  | Not Started |  | Yes

## 07_Executive_Dashboard
TIB Controls Executive Dashboard
KPI | Value |  | Executive Summary / Decisions Required
Overall Status | Amber |  | Use this area to explain: What happened? Why does it matter? What are we doing? Who owns it? When will it be resolved? What decision is required from management?
Scope Confirmed % | 87
Controls Identified | 142
Testing Complete % | 61
Evidence Overdue | 17
High/Critical Deficiencies | 3
Top Risk / Issue | Impact | Owner | Due | Status | Decision Needed | Escalation | Next Update

## 08_30_60_90_Roadmap
Controls Lead 30 / 60 / 90-Day Roadmap
Horizon | Objective | Key Actions | Deliverables | Stakeholders | Success Measure | Risk / Dependency | Status
0-30 Days | Stabilize and understand | Validate scope, team, artifacts, deadlines, audit requests and immediate risks. | 30-Day Assessment; RACI; status dashboard | Sponsor; Audit; IT; Finance | No unknown critical deadlines; clear ownership | Incomplete inherited documentation | Not Started
31-60 Days | Improve delivery quality | Strengthen QA, evidence flow, testing governance, remediation ownership and reporting. | QA cadence; remediation plan; improved dashboard | Workstream leads; control owners | Reduced rework and overdue evidence | Resource/capacity constraints | Not Started
61-90 Days | Institutionalize governance | Embed sustainable controls governance, metrics, continuous monitoring opportunities and improvement roadmap. | 90-Day roadmap; governance calendar; automation opportunities | CIO/CFO/IA; process owners | Stable cadence; transparent risks; accepted roadmap | Competing transformation priorities | Not Started